## Sheet1
PROJECT NUMBER | 35
PROJECT NAME | Cross-Channel Customer Interest & Engagement Intelligence System
PROJECT MENTOR (sponsor) | Meera Rajagopalan
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Sian | 0.25 | 0.15 | Done |  | 0.1
Client meeting | Coordination | Kushagra | 1 | 0.5 | Done | Introduction and basic plan discussed | 0.5
Project synopsis writeup | Documentation | Kaushik | 1 | 0.75 | Done |  | 0.25
Decide Tech-Stack | Documentation | Srinivas | 1.5 | 1 | Done |  | 0.5
Minutes of Meeting | Documentation | Devshree | 0.5 | 0.3 | Done |  | 0.2
Team Meeting | Coordination | Kushagra | 1 | 0.5 | Done | To search more on APIs to get data and methods to get insightful stats | 0.5
Week 2 (January 22 - January 28) | [6 empty] | 0
Client meeting | Coordination | All | 0.5 | 0.4 | Done |  | 0.1
Minutes of Meeting | Documentation | Kushagra | 0.5 | 0.3 | Done |  | 0.2
Creating the Prototype UI | Preparation | Srinivas |  |  |  |  | 0
GIT Repository setup | Preparation | Kaushik | 0.25 | 0.2 | Done |  | 0.05
Team Meeting | Coordination | All | 0.75 | 0.5 | Done | Decided on Prototyping Process Model | 0.25
Week 3 (January 29 - February 4) | [6 empty] | 0
Client meeting | Coordination | All | 1 | 1.25 | Done | Discussion about what all is possible and out of scope things and the improvements of prototype | -0.25
Minutes of Meeting | Documentation | Sian | 0.5 | 0.3 | Done |  | 0.2
Team Meeting | Coordination | All | 0.75 |  | Pending |  | 0.75
Status tracker | Documentation | Devshree | 2 | 1.75 | Done |  | 0.25
Research on Data availibility on different platforms: | Preparation
Youtube, Google Ads |  | Sian | 1 |  | Pending
Facebook/Instagram |  | Devshree | 1 |  | Pending
Search/SEO, Blog Entries |  | Kushagra | 1 |  | Pending
LinkedIn - Co-Founders and Company Pages |  | Kaushik | 1 |  | Pending
Email Campaigns, E-Commerce |  | Srinivas | 1 |  | Pending
Week 6